## Gantt Chart
IT 351 Computer Networks Project — Gantt Chart
Project Start | 2026-07-19 | Phase 1 Submission | 2026-07-26 | Final Submission | 2026-08-09
Course | DS360 - Computer Networks | Project | Campus WAN & LAN Infrastructure Setup
Task Name | Assigned To | Start | End | Duration | Depends On | 19-Jul | 20-Jul | 21-Jul | 22-Jul | 23-Jul | 24-Jul | 25-Jul | 26-Jul | 27-Jul | 28-Jul | 29-Jul | 30-Jul | 31-Jul | 01-Aug | 02-Aug | 03-Aug | 04-Aug | 05-Aug | 06-Aug | 07-Aug | 08-Aug | 09-Aug
Setup GitHub Repository & Google Doc Live Artifacts | Mansour | 2026-07-19 | 2026-07-20 | 2 | None | bar: 19-Jul to 20-Jul
Task 1: Cisco Packet Tracer Installation & System Screenshot | Member 2 | 2026-07-20 | 2026-07-22 | 3 | Setup GitHub Repository & Google Doc Live Artifacts | bar: 20-Jul to 22-Jul
Task 2: Objectives & Advantages of Packet Tracer Study | Member 3 | 2026-07-21 | 2026-07-23 | 3 | Task 1: Cisco Packet Tracer Installation & System Screenshot | bar: 21-Jul to 23-Jul
Task 3: IP Addressing Scheme Decisions & Encountered Problem | Member 2 | 2026-07-23 | 2026-07-24 | 2 | Task 2: Objectives & Advantages of Packet Tracer Study | bar: 23-Jul to 24-Jul
Phase 1 Mid-Progress Report Compilation & Submission (Deadline 26/07) | Mansour | 2026-07-25 | 2026-07-26 | 2 | Task 3: IP Addressing Scheme Decisions & Encountered Problem | bar: 25-Jul to 26-Jul
Phase 2: WAN 1 & WAN 2 Topology Design (Switches & End Devices) | Member 2 | 2026-07-27 | 2026-07-30 | 4 | Phase 1 Mid-Progress Report Compilation & Submission (Deadline 26/07) | bar: 27-Jul to 30-Jul
Phase 2: IP Addressing & Router Interfaces Configuration | Member 3 | 2026-07-31 | 2026-08-03 | 4 | Phase 2: WAN 1 & WAN 2 Topology Design (Switches & End Devices) | bar: 31-Jul to 03-Aug
Phase 2: Enable Static/RIP Routing over Serial Link | Member 2 | 2026-08-04 | 2026-08-06 | 3 | Phase 2: IP Addressing & Router Interfaces Configuration | bar: 03-Aug to 05-Aug
Phase 2: Cross-WAN Ping Connectivity Testing & Packet Analysis | Member 3 | 2026-08-07 | 2026-08-08 | 2 | Phase 2: Enable Static/RIP Routing over Serial Link | bar: 06-Aug to 07-Aug
Final Project Report & Packet Tracer (.pkt) Submission | Mansour | 2026-08-08 | 2026-08-09 | 2 | Phase 2: Cross-WAN Ping Connectivity Testing & Packet Analysis | bar: 07-Aug to 08-Aug